## Sheet1
S.No.	Work	Dependency	Status
1	Set up local environment for Tensorflow to run	None	Finished

2	Research paper comprehension for social credit risk analysis	None	Finished

3	Worked on cleaning the available Gullakh data,removing outliers,dropping invalid columns etc	None	Finished

4	Extraction of transaction details from bank statements of SBI bank	None	Finished

5	Converting extracted transaction details into Json for SBI bank	None	Finished

6	Extracting user details from bank statement pdf using Poppler and Tabula	No UI available to get the exact coordinates of the text to be extracted	Awaited

7	Scraping data from Zaubacorp website	None	Finished

8	Scraping data from Instafinancials website	Website uses EV certificate, even Tor cannot access it, stuck at ReCaptcha	Stalled

9	Social login page for Gullakh	Further work to be done by UI dev	Finished

10	Setting up validations for IIFL form	Furher work to be done by UI dev	Finished

11	Copying current address to permanent address IIFL form debugging	Minor issue to be resolved by the CTO	Finished

12	Developing Python script to calculate Twitter score	None	Finished

13	To develop python scripts for google,fb,instagram scores	Awaiting auth permissions	Awaited

14	Integrated tor support in selenium to scrape web pages	None	Finished

15	Integrated OCR librarry to scrape PDF pages	None	Finished

16	Php backend integration of python social scoring scripts	Held up by Suneel Sir	In progress

17	Researched IBM Insights API, Extracta , Friendly Score, PIPL docs	None	Finished

18	Attended multiple meetings including IBM, Friendly Score	None	Finished

19	Learnt AWS SageMaker mechanisms	None	Finished

20	Incorporated inintial form provided by Akbar Sir into gullakh webpage	None	Finished

21	Restructured IIFL form as they were many missing fields, incorrect label names, missing placeholders	None	Finished

22	Tested the ahaloans statement analyser API on Postman and Python	None	Finished

23	Developed the Meet the Team page of Ahaloans	Text wrapping to be looked at by higher authority	Finished