## Sheet1
S. No. | Work | Dependency | Status
1 | Research paper comprehension and formulations | None from company’s end | Completed
2 | Initial machine learning doc | None from company’s end | Completed
3 | Initial machine learning model | Data reduced by a margin due to PIPL, Towerdata dependency | Stalled
4 | Social Score project doc | None from company’s end | Completed
5 | Social login page on Gullakh design and integration | Further work by UI developer | Completed
6 | Scraping InstFiinancial | Instafinancial secured by EV security and also by Google Capcha | Stalled
7 | Social score project | Facebook, Instagram, Google permission required | Waiting
8 | IIFL form verification debug and received form structure was restructured | None from company’s end | Completed
9 | Copying current address to permanent address | Minor issue to be resolved by CTO | Completed
10 | Social score twitter backend | None from company’s end | Completed
11 | Social score linkedin backend | None from company’s end | By the end of the week
12 | Finding if ICICI statement is detailed or not | None from company’s end | Completed
13 | Received Gullakh data cleaning | None from company’s end | Completed
14 | Machine learning model architecture roadmap | None from company’s end | Completed
15 | Backend PHP and Python connection | Held up by Suneel sir | To be completed
16 | Social score logic | None from company’s end | Completed
17 | Read IBM, Pipl, FriendlyScore, Extracta, FullContact developer docs | None from company’s end | Completed
18 | Multiple meeting including IBM, FriendlyScore, Extracta etc attended | None from company’s end | Completed
19 | AWS SageMaker setup | None from company’s end | Completed
20 | Friendlyscore reverse engineering | None from company’s end | Completed